## FTE Plan
HEX Aero Team FTE & Hours Forecast
4x10 schedule (Mon-Thu). Yellow cells are inputs; everything else computes automatically.
Inputs
Start month | 2026-08-01 | Company holiday dates are entered in the Holidays table at the bottom of the sheet.
Number of months (1-12) | 5
Hours per workday | 10
Calendar (auto-computed)
Month |  |  |  | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | [7 empty] | Total
Workdays (Mon-Thu) |  |  |  | 17 | 18 | 17 | 17 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88
Holidays in month |  |  |  | 0 | 1 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
Net workdays |  |  |  | 17 | 17 | 17 | 16 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
Available hours per 1.0 FTE |  |  |  | 170 | 170 | 170 | 160 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810
Role hours by month
Role | Description | Avg FTE/wk | Months needed | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | [7 empty] | Total hrs
Aero lead | Interfaces across disciplines; owns aero requirements and responsibilities; task allocation; leads meetings; keeps program on track; handles inbound aero requests | 0.5 |  | 81 | 81 | 81 | 81 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405
Vehicle configuration engineer | Keeps model up to date; tracks changes; CAD cleanup; prepares geometry for FEA; main POC with airframe/structures | 0.1 |  | 16.2 | 16.2 | 16.2 | 16.2 | 16.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
Component analysis engineer | Interfaces with loads & criteria; incorporates model changes; runs component-level analyses to ensure proper sizing/design | 0.5 |  | 81 | 81 | 81 | 81 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405
Vehicle point performance analysis engineer | Full-vehicle performance analysis; integrates design changes; runs StarCCM+ and Helios across operating conditions; owns StarCCM+ meshing | 0.5 |  | 81 | 81 | 81 | 81 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405
Maneuver analysis engineer | Runs maneuver/trim analyses in the framework | 0.1 |  | 16.2 | 16.2 | 16.2 | 16.2 | 16.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
Maneuver framework engineer | Maintains maneuver framework; integrates model/mesh updates; interfaces with rotors, handling qualities, loads & criteria, mass properties | 0.1 |  | 16.2 | 16.2 | 16.2 | 16.2 | 16.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
Aero thermal engineer | Interfaces with thermal team; momentum drag calculations; aero-thermal integration | 0.2 |  | 32.4 | 32.4 | 32.4 | 32.4 | 32.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162
Mesh engineer | Surface mesh in StarCCM+ from model updates; volume mesh in Pointwise for Helios/maneuver; distributes meshes and tracks status (bursty workload) | 0.1 |  | 16.2 | 16.2 | 16.2 | 16.2 | 16.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Team total |  | 2.1 |  | 340.2 | 340.2 | 340.2 | 340.2 | 340.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1701
Monthly allocation percentages (per role) | Share of each role's total hours landing in each month. Percentages over the role's active months must sum to 100% — the Check column flags anything else. Months beyond a role's "Months needed" are ignored.
Role |  |  | Check | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Aero lead |  |  | OK | 20% | 20% | 20% | 20% | 20%
Vehicle configuration engineer |  |  | OK | 20% | 20% | 20% | 20% | 20%
Component analysis engineer |  |  | OK | 20% | 20% | 20% | 20% | 20%
Vehicle point performance analysis engineer |  |  | OK | 20% | 20% | 20% | 20% | 20%
Maneuver analysis engineer |  |  | OK | 20% | 20% | 20% | 20% | 20%
Maneuver framework engineer |  |  | OK | 20% | 20% | 20% | 20% | 20%
Aero thermal engineer |  |  | OK | 20% | 20% | 20% | 20% | 20%
Mesh engineer |  |  | OK | 20% | 20% | 20% | 20% | 20%
Company holidays (exact dates) | Company-wide days off. Only dates landing on a Mon-Thu inside the forecast window are counted. 20 slots; leave unused blank.
Holiday | Date
Labor Day | 2026-09-07
Thanksgiving | 2026-11-26
Winter shutdown | 2026-12-24
Winter shutdown | 2026-12-28
Winter shutdown | 2026-12-29
Winter shutdown | 2026-12-30
Winter shutdown | 2026-12-31
Note on A27: Spare rows: type a role name and FTE here to add a role, then set its monthly percentages below.
Note on B5: First day of the first forecast month
Note on D18: How many months (from the start month) this role is needed. Leave blank for the full forecast duration.